## Summary
Fixture — invented values, same shape as a real mobilisation pack
A view, not a register.

## Tasks
Fixture — invented values, same shape as a real mobilisation pack
Yellow columns maintained by the PM.
ACME · FIXTURE-001 v1.0 · 1 Oct – 1 Dec 2026
ID | Week | Owner | Task | Gate/Control | Due | Depends on | Status | Note
T-001 | B1 | PM | Access check for all consultants | DP-B01 | 1 Oct |  | Not started
T-002 | B1 | Lead | Take the baseline extract | G1 | 3 Oct | T-001 | In progress
T-003 | B2 | Lead | Load the picklist option set | G2 | 10 Oct | T-002; T-001 | Complete

## Gates
Fixture — invented values, same shape as a real mobilisation pack
Yellow columns maintained by the PM.
ACME · FIXTURE-001 v1.0 · 1 Oct – 1 Dec 2026
Gate | Name | Date | Criteria | Evidence | Approver | Passed
G1 | Baseline accepted | Fri 9 Oct | Baseline extract taken and accepted | Baseline manifest; profiling report | Lead + client IT owner
G2 | Foundation signed | Fri 23 Oct | Foundation objects verified in QAL | Verification report | Client IT owner
G3 | Hypercare entry | week 8 | Support model accepted | Signed RACI | Client IT owner
One-way doors
# | Door | When | Control | Approver | Executed
D1 | Foundation freeze | Fri 16 Oct | Design authority sign-off | Lead
D2 | Production data load | Sat 28 Nov | Two-person rule | Load lead + client IT

## Decisions
Fixture — invented values, same shape as a real mobilisation pack
Yellow columns maintained by the PM.
ACME · FIXTURE-001 v1.0 · 1 Oct – 1 Dec 2026
DP | Decision | Owner | GONXT position | Due | Status
DP-B01 | Which legal entities are in scope | Client IT owner | The four trading entities only | 3 Oct | Open
DP-B02 | Pay frequency for monthly staff | Client payroll | Monthly, last working day | 10 Oct | Open

## Conditions
Fixture — invented values, same shape as a real mobilisation pack
Yellow columns maintained by the PM.
ACME · FIXTURE-001 v1.0 · 1 Oct – 1 Dec 2026
# | Condition | By | Consequence if it fails
1 | DEV and QAL instances provisioned | 1 Oct | Week 1 cannot start; day-for-day slip
2 | Legacy read-only access granted | 1 Oct | No baseline extract; G1 cannot pass

## KT Tracker
Fixture — invented values, same shape as a real mobilisation pack
Yellow columns maintained by the PM.
ACME · FIXTURE-001 v1.0 · 1 Oct – 1 Dec 2026
# | Week | With | Competence check | Evidence | Status | Signed by / date
K1 | B1 | Lead | Explains why the baseline extract is taken first | Verbal check + screenshot | Not started

## Deliverables
Fixture — invented values, same shape as a real mobilisation pack
Yellow columns maintained by the PM.
ACME · FIXTURE-001 v1.0 · 1 Oct – 1 Dec 2026
# | Deliverable | Draft due | Validated by | Accepted by | Final due | Status
D1 | Support model and RACI | 9 Oct | Walkthrough with the IT owner | Client IT owner | 27 Nov | Not started
D2 | Configuration workbook | 25 Oct | Design authority review | Lead | 8 Jan | Not started